## CBA
|  | Year 1 ($) | Year 2 ($) | Year 3 ($) | Year 4 ($) | Year 5 ($) | Total
Benefits
110 | Increased Revenues | 0 | 56000 | 78400 | 109760 | 153664
111 | Increased Sales | 0 | 75000 | 112500 | 168750 | 253125
114 | Decreased Administrative Costs | 0 | 42000 | 43260 | 44557.8 | 45894.534
115 | Customer Retention | 0 | 15000 | 15750 | 16537.5 | 17364.375
| Total Benefits | 0 | 188000 | 249910 | 339605.3 | 470047.909 | 1247563.209
Development costs
211 | Labor: Project Manager | 10200 | - | - | - | -
212 | Labor: Business Analyst | 14400 | - | - | - | -
213 | Labor: Senior Developer 1 | 19200 | - | - | - | -
214 | Labor: Web Designer/Content Manager | 4800 | - | - | - | -
215 | Labor: Application Developer | 8320 | - | - | - | -
216 | Labor: Quality Control | 3200 | - | - | - | -
219 | DBA (one-time) + capital equipment & licenses | 22887 | - | - | - | -
| Total development costs | 83007 | 0 | 0 | 0 | 0 | 83007
Operational costs
311 | Software license and renewal | - | 3400 | 3072 | 3072 | 3072
312 | Hosting and Infrastructure | - | 12000 | 12000 | 12000 | 12000
313 | Database Adminstrator | - | 3006 | 3006 | 3006 | 3006
314 | Backup & Disaster Recovery | - | 2200 | 2200 | 2200 | 2200
315 | Training & Documentations | - | 3500 | 3500 | 3500 | 3500
316 | Security Measures | - | 3400 | 3400 | 3400 | 3400
317 | Regulatory Compliance | - | 3200 | 3200 | 3200 | 3200
| Total operational costs | 0 | 30706 | 30378 | 30378 | 30378 | 121840
401 | Total costs | 83007 | 30706 | 30378 | 30378 | 30378 | 204847
402 | Net benefits | -83007 | 157294 | 219532 | 309227.3 | 439669.909 | 1042716.209
403 | Cumulative Net Cash Flow | -83007 | 74287 | 293819 | 603046.3 | 1042716.209
Payback Period = YEAR 2
Comments
This sheet summarizes the 5-year financial feasibility. Year 1 captures one-time development cost, Years 2-5 include recurring operational costs, and benefits are calculated from revenue growth and cost-saving assumptions in the DETAILS sheet. Read Total Costs, Net Benefits, and Cumulative Net Cash Flow together to confirm financial viability and payback timing.
Conclusion
Conclusion: Financially feasible. Year 1 total cost = USD 83,007; Year 2 net benefit = USD 157,294; cumulative net cash flow by Year 5 = USD 1,042,716.21; payback occurs in Year 2.
|  |  | 56000 | 78400 | 109760 | 153664
|  |  | 75000 | 105000 | 147000 | 205500
|  |  | 42000 | 44100 | 46200

## DETAILS
|  | LY Revenue | Increase % | Total Increase Year 2 | Year 3 | Year 4 | Year 5
110 | Increased Revenues | 40000 | 0.4 | 56000 | 78400 | 109760 | 153664
111 | Increased Sales | 50000 | 0.5 | 75000
**Incremental increase in revenue per year, starting with Year 2 (40% increase over LY), then (40% increase YoY)
|  | Rate | Total # of Hours | Total Amount | Description | Source
211 | Labor: Project Manager | 100 | 102 | 10200 | 512*0.2 | https://www.coursera.org/articles/project-manager-salary
212 | Labor: Business Analyst | 90 | 160 | 14400 | 2hrs/day/4months | https://www.glassdoor.co.in/Salaries/united-states-business-analyst-salary-SRCH_IL.0,13_IN1_KO14,30.htm#:~:text=The%20average%20additional%20cash%20compensation%20for%20a%20Business,Glassdoor%20by%20Business%20Analyst%20employees%20in%20United%20States.
213 | Labor: Senior Developer 1 | 150 | 128 | 19200 | 8hr/week/4months | Compensation Management Solution - CompAnalyst ¦ Salary.com
214 | Labor: Web Designer/Content Manager | 75 | 64 | 4800 | 4hr/week/4months | https://www.coursera.org/articles/project-manager-salary
215 | Labor: Application Developer | 65 | 128 | 8320 | 8hrs/week/4month | https://www.ziprecruiter.com/Salaries/Software-Applications-Developer-Salary-in-Washington,DC
216 | Labor: Quality Control | 100 | 32 | 3200 | 8hrs/month/4month | Salary: Quality Assurance Manager in United States 2024 ¦ Glassdoor
304 | DBA | 160 | 80 | 12800 | 5hr/week/4months
|  | No of Items | Rate | Total Sum |  | Source
216 | Ipads | 3 | 429 | 1287 |  | https://www.amazon.com/dp/B0BJLXMVMV?tag=track-ect-bing-usa-187242-20&linkCode=osi&th=1&psc=1
217 | Monthly Subcriptions | 200 | 4months | 800 |  | https://www.hostgator.com/promo/top10best?clickid=3CvXjzSBzxyNTz%3ARtMS-yR5NUkH1ejwmIzLezo0&irgwc=1&affpat=1&mpid=34020&utm_source=IR&utm_medium=affiliate&utm_campaign=Natural%20Intelligence%20LTD%2C&channelid=P61C46098237S645N0B2A20D0E0000V100&siteID=46098437&irpid=34020
218 | Desktops | 6 | 1000 | 6000 |  | Amazon.com: LG Gram 17" WQXGA Intel Evo Platform Laptop, 13th Gen Intel i7-1360P Processor, 16GB RAM, 2TB SSD, Webcam, Bluetooth, USB-C, Backlit Keyboard, Windows 11, School and Business Ready, LIONEYE Bundle : Electronics
220 | SQL Server License | n/a | n/a | 2000 |  | Microsoft SQL Server 2019 Standard + 10 CALs (trustedtechteam.com)
|  | Year 2 | Year 3 | Year 4 | Year 5
311 | Software license and renewal | 3400 | 3072 | 3072 | 3072 | 2 Operating system/$200/server, Database software $2000, & Development tools framework1000
312 | Hosting and Infrastructure | 12000 | 12000 | 12000 | 12000 | Cloud hosting services (Google Cloud): $500/month/Dedicated server 500/month
313 | Database development and Maintenance | 3006 | 3006 | 3006 | 3006 | 5% of development cost annually 0.05*60120
314 | Backup & Disaster Recovery | 2200 | 2200 | 2200 | 2200 | Backup solutions $100/month/12 ,Recovery planning and periodic testing 1000/yr
315 | Training & Documentations | 3500 | 3500 | 3500 | 3500 | Document creation and meaintenance $1500/qtr, training cost/ qtr $2000
316 | System Security Subscription | 3400 | 3400 | 3400 | 3400 | Security Software and tools $200/month , Regular security Audit $1000/audit/yr
317 | Regulatory Compliance | 3200 | 3200 | 3200 | 3200 | Legal consultations 8hrs/qtr @ $100/hr
Comments
This sheet documents the assumptions behind every cost and benefit input used in the CBA. It shows labor effort, rates, infrastructure/tooling costs, and operating costs by year, with source references for traceability. Update this sheet first when assumptions change; linked CBA totals will update accordingly.
Conclusion
Conclusion: Assumptions are internally consistent and traceable. Labor estimate = USD 72,920; one-time tools/equipment/licenses = USD 10,087; recurring operating costs = USD 30,706 (Year 2), 30,378 (Year 3), 30,378 (Year 4), and 30,378 (Year 5).

## Risk Analysis
Questions | Answer | Rating
How long will it take to implement the proposed project | 1 to 6 months | 1
What are the estimated project costs | USD 75,000 to USD 250,000 | 1
Degree of anticipated change to existing business processes: | High | 100
Number of employees impacted by the system | 1 to 20 | 1
Number of agencies impacted by the system | four to Eight | 100
Anticipated user attitude to the new process/system: | Neutral | 100
Number of existing applications that must feed or receive data from the new system | 0 | 1
Volume of required data to be converted from existing system to new system: | None | 1
Complexity of the required conversion | No Conversion Required | 1
Will the system be implemented with an off-the-shelf system | No | 500
Has the Titans Food developed/implemented system similar in size and complexity in the past | No | 500
Project teams level of experience with the business process being impacted | Medium | 100
Titans Food staffs experience with implementing systems with similar technologies | Low | 250
Support of Department Head (s) and Senior Managers in the impacted agencies | High | 1
Other external entity, such as the State, is involved in the project | External Entity is Playing a Minnor Roles | 250
Comments
This sheet scores delivery risk using the weighted ratings in column C. The project score is automatically calculated from C2:C16, and the risk status line is formula-driven from that score range. To reassess risk, update answers/ratings only; score and status update automatically.
Conclusion