## Document Map
SDLC Phase | Document | File | Aligns to
01 Initiation | PID | PID-Project-Initiation-Document-v4.0.pdf | Scope, objectives
01 Initiation | Feasibility / CBA | Feasibility-Study-and-Cost-Benefit-Analysis-v4.0.xlsx | Business case
02 Planning | PMP | Project-Management-Plan-and-Governance-v4.0.pdf | Governance, sign-off
03 Requirements | SRS | SRS-Software-Requirements-Specification-v4.0.pdf | FR, AUTH, NFR
03 Requirements | DRD | DRD-Data-Requirements-Document-v4.0.pdf | DR 2.x, 3.x
03 Requirements | RTM | RTM-Requirements-Traceability-Matrix-v4.0.xlsx | This workbook
03 Requirements | UCS | UCS-Use-Case-Specification-v4.0.pdf | UC 1.x-2.x
04 Design | SDD | SDD-System-Design-and-Architecture-v4.0.pdf | Architecture
04 Design | DDD | DDD-Logical-Data-Dictionary-v4.0.pdf | Entities
04 Design | ADD | ADD-API-Design-Standards-v4.0.pdf | API standards
04 Design | Diagrams | diagrams/*.png | Context, ERD, states
05 Testing | STP | STP-System-Test-Plan-v4.0.xlsx | TC-* test cases
05 Testing | QAP | QAP-Quality-Assurance-Plan-v4.0.pdf | QA approach
06 Operations | ORD | ORD-Operations-Requirements-and-SLA-v4.0.pdf | DRRD, SLA
Agile | PVR | PVR-Product-Vision-and-Release-Plan-v4.0.pdf | R1/R2 roadmap
Agile | PBL | PBL-Product-Backlog-Master-v4.0.xlsx | User stories
Agile | DOD | DOD-Definition-of-Done-v4.0.pdf | Done criteria
Agile | SBL | SBL-Sprint-Backlog-Template-v4.0.xlsx | Sprint execution
Agile | ACT | ACT-Agile-Ceremony-Templates-v4.0.xlsx | Scrum ceremonies
04 Design | API Contract | API-REST-Contract-Specification-v4.0.pdf | REST endpoints
02 Planning | IRC | Implementation-Readiness-Checklist-v4.0.pdf | Dev start gate
02 Planning | Sign-Off | Production-Sign-Off-Register-v4.0.xlsx | Approvals
04 Design | API Contract (Excel) | API-REST-Contract-v4.0.xlsx | Postman/DevOps import; pairs with PDF

## MVP Functional
Req ID | DR | Entities | UC | TC ID | Phase | Status | User Story
FR1 | 2.1 | Customer | UC 1.1 | TC-FR1 | MVP | Planned | US-001
FR2 | 2.1, 2.2 | Customer | UC 1.2 | TC-FR2 | MVP | Planned | US-002
FR3 | 2.1 | Customer | UC 1.5 | TC-FR3 | MVP | Planned | US-003
FR4 | 2.2, 2.3 | Customer, Order | UC 1.1+ | TC-FR4 | MVP | Planned | US-004
FR5 | 2.9, 3.0 | Item, Menu | UC 2.5 | TC-FR5 | MVP | Planned | US-020
FR6 | 2.9 | Item | UC 2.5 | TC-FR6 | MVP | Planned | US-020
FR7 | 2.9, 3.0 | Item | UC 2.7 | TC-FR7 | MVP | Planned | US-020
FR8 | 2.3, 2.9 | Order, OrderHasItems, Item | UC 1.8 | TC-FR8 | MVP | Planned | US-011
FR9 | 2.3 | OrderHasItems | UC 2.0 | TC-FR9 | MVP | Planned | US-011
FR10 | 2.3 | OrderHasItems | UC 1.9 | TC-FR10 | MVP | Planned | US-011
FR11 | 2.3 | OrderHasItems | UC 1.8 | TC-FR11 | MVP | Planned | US-011
FR12 | 2.3 | OrderHasItems | UC 1.9 | TC-FR12 | MVP | Planned | US-011
FR13 | 2.1 | Payment | UC 2.2 | TC-FR13 | MVP | Planned | US-012
FR14 | 2.1 | Payment, Customer | UC 2.2 | TC-FR14 | MVP | Planned | US-012
FR15 (Retired) | - | - | - | N/A | - | Retired | -
FR16 | 2.3 | Payment, Order | UC 2.2 | TC-FR16 | MVP | Planned | US-012
FR17 | 2.3, 2.6 | Order, Delivery | UC 2.3 | TC-FR17 | MVP | Planned | US-013
FR18 | 2.3 | Order | UC 2.1 | TC-FR18 | MVP | Planned | US-013
FR19 | 2.9 | Item | UC 1.6 | TC-FR19 | MVP | Planned | US-010
FR20 | 2.2, 2.9 | Item, Customer | UC 1.6 | TC-FR20 | MVP | Planned | US-010
FR21 | 3.0 | Order | UC 2.8 | TC-FR21 | MVP | Planned | US-021
FR22 | 3.0 | Order, Item | UC 2.8 | TC-FR22 | MVP | Planned | US-021
FR23 | 2.3 | Order | UC 1.7 | TC-FR23 | MVP | Planned | US-011
FR24 | 2.9 | Menu, Item | UC 1.6 | TC-FR24 | MVP | Planned | US-010
FR25 | 2.3 | Payment, Order | UC 2.6 | TC-FR25 | MVP | Planned | US-021
FR26 | 3.0 | Item | UC 2.7 | TC-FR26 | MVP | Planned | US-020
FR27 | 3.0 | Item | UC 2.7 | TC-FR27 | MVP | Planned | US-020
FR28 | 2.7 | Order | UC 2.9 | TC-FR28 | MVP | Planned | US-021
FR29 | 3.0 | Order | UC 2.8 | TC-FR29 | MVP | Planned | US-021
FR30 | 2.7 | Order | UC 2.9 | TC-FR30 | MVP | Planned | US-022
AUTH-01 | 3.1 | Employee, Customer | UC 1.3, 2.4 | TC-AUTH-01 | MVP | Planned | US-030

## R2 Functional
Req ID | TC ID | Phase | User Story | Status
FR31 | TC-FR31 | R2 | US-101 | Planned
FR32 | TC-FR32 | R2 | US-101 | Planned
FR33 | TC-FR33 | R2 | US-101 | Planned
FR34 | TC-FR34 | R2 | US-101 | Planned
FR35 | TC-FR35 | R2 | US-101 | Planned
FR36 | TC-FR36 | R2 | US-101 | Planned
FR37 | TC-FR37 | R2 | US-101 | Planned
FR38 | TC-FR38 | R2 | US-101 | Planned
FR39 | TC-FR39 | R2 | US-101 | Planned
FR40 | TC-FR40 | R2 | US-101 | Planned
FR41 | TC-FR41 | R2 | US-101 | Planned
FR42 | TC-FR42 | R2 | US-101 | Planned
FR43 | TC-FR43 | R2 | US-101 | Planned
FR44 | TC-FR44 | R2 | US-101 | Planned
FR45 | TC-FR45 | R2 | US-101 | Planned
FR46 | TC-FR46 | R2 | US-101 | Planned
FR47 | TC-FR47 | R2 | US-101 | Planned
FR48 | TC-FR48 | R2 | US-101 | Planned
FR49 | TC-FR49 | R2 | US-101 | Planned
FR50 | TC-FR50 | R2 | US-101 | Planned

## NFR
Req ID | System refs | TC ID | Verification method | User Story
NFR1 | SAR1 | TC-NFR1 | MFA enrollment test (admin mandatory) | US-040
NFR2 | SAR2, NFSR2 | TC-NFR2 | Audit log inspection | US-040
NFR3 | NFSR1, DRRD7 | TC-NFR3 | Security scan / TLS check | US-040
NFR4 | - | TC-NFR4 | Load test report | US-040
NFR5 | SLA | TC-NFR5 | Uptime monitoring 30 days | US-040
NFR6 | DBRRD1 | TC-NFR6 | Backup restore drill | US-041
NFR7 | - | TC-NFR7 | Cross-device UI checklist | US-040
NFR8 | - | TC-NFR8 | Usability session (SUS) | US-040
NFR9 | - | TC-NFR9 | Navigation walkthrough | US-040
NFR10 | FR13 | TC-NFR10 | Gateway webhook idempotency test | US-040
NFR11 | - | TC-NFR11 | Architecture scalability review | US-040
NFR12 | - | TC-NFR12 | Performance test (menu, checkout) | US-040
NFR13 | - | TC-NFR13 | Admin dashboard latency <= 10s | US-040
NFR14 | - | TC-NFR14 | Browser smoke: Chrome | US-040
NFR15 | - | TC-NFR15 | Browser smoke: Edge | US-040
NFR16 | - | TC-NFR16 | Browser smoke: Firefox | US-040
NFR17 | - | TC-NFR17 | Browser smoke: Safari | US-040
NFR18 | FR19 | TC-NFR18 | Search timing p95 <= 3s | US-040
NFR19 | - | TC-NFR19 | iOS mobile web smoke | US-040
NFR20 | - | TC-NFR20 | WCAG 2.1 AA audit | US-040
NFR21 | DR | TC-NFR21 | Failover drill | US-040

## Retention System
Req ID | FR/NFR supported | TC ID | User Story
DRRD1-7 | FR3, FR18, legal retention | TC-SYS-RET | US-041
DBRRD1 | NFR6 | TC-NFR6 | US-041
NFSR1-5 | FR13, AUTH-01 | TC-NFR3, TC-AUTH-01 | US-041
SAR1-3 | NFR1, NFR2 | TC-NFR1, TC-NFR2 | US-041

## Production Readiness
Criterion | Status | Evidence
No broken .md/yaml references in PDFs | Pass | Production build
API contract self-contained PDF | Pass | API-REST-Contract-Specification-v4.0.pdf
STP covers all RTM TC IDs | Pass | Alignment validation
FR15 retired | Pass | SRS + RTM
Sign-off register present | Pass | Production-Sign-Off-Register-v4.0.xlsx