## Test Plan
TestCaseID | RequirementID | Release | TestSteps | ExpectedResult | Status | Comments | TestDate | Tester
TC-AUTH-01 | AUTH-01 | MVP | 1. Open login. 2. Enter valid username/password. 3. Submit. | User authenticated and routed to role-appropriate home. | Planned
TC-FR1 | FR1 | MVP | 1. Navigate to registration. 2. Enter name, email, phone, password. 3. Submit. | Account created; verification sent if enabled. | Planned
TC-FR2 | FR2 | MVP | 1. Log in. 2. Open profile. 3. Change phone. 4. Save. | Profile shows updated phone. | Planned
TC-FR3 | FR3 | MVP | 1. Log in. 2. Request account deletion. 3. Confirm. | Account disabled; PII handled per retention policy. | Planned
TC-FR4 | FR4 | MVP | 1. Complete one order. 2. Open home/recommendations. | Recommendations or empty-state shown from history. | Planned
TC-FR5 | FR5 | MVP | 1. Admin login. 2. Add menu item with price. 3. Save. | Item visible on customer menu. | Planned
TC-FR6 | FR6 | MVP | 1. Admin marks item unavailable. 2. Customer views menu. | Item hidden or not addable. | Planned
TC-FR7 | FR7 | MVP | 1. Admin links promotion to item. 2. Customer views item. | Discount reflected at item/checkout. | Planned
TC-FR8 | FR8 | MVP | 1. Customer adds item with qty 2. 2. View cart. | Line shows qty 2 and correct subtotal. | Planned
TC-FR9 | FR9 | MVP | 1. Change qty in cart. 2. Proceed toward checkout. | Cart reflects changes. | Planned
TC-FR10 | FR10 | MVP | 1. Add item. 2. Navigate to another page. | Cart badge/summary still visible. | Planned
TC-FR11 | FR11 | MVP | 1. Add items. 2. Save for later. 3. Re-login. | Saved cart restored. | Planned
TC-FR12 | FR12 | MVP | 1. Remove item from cart. | Cart empty or remaining items only. | Planned
TC-FR13 | FR13 | MVP | 1. Checkout with test card. 2. Complete payment. | Gateway success; order marked paid; no clear-text PAN stored. | Planned
TC-FR14 | FR14 | MVP | 1. Open payment methods. 2. Add/update via gateway. 3. Save. | Only token/last-four shown. | Planned
TC-FR16 | FR16 | MVP | 1. Complete payment. 2. Query order payment record. | Payment.OrderID matches order. | Planned
TC-FR17 | FR17 | MVP | 1. Place order. 2. Admin advances status. 3. Customer refreshes status. | Status updates within 30 seconds. | Planned
TC-FR18 | FR18 | MVP | 1. Open order history. | Past orders listed newest first. | Planned
TC-FR19 | FR19 | MVP | 1. Search menu keyword. | Results within 3 seconds. | Planned
TC-FR20 | FR20 | MVP | 1. Apply price/diet filter. | Filtered list matches criteria. | Planned
TC-FR21 | FR21 | MVP | 1. Admin runs weekly sales report. | Totals match order data. | Planned
TC-FR22 | FR22 | MVP | 1. Admin opens popularity report. | Top items listed for period. | Planned
TC-FR23 | FR23 | MVP | 1. Checkout select pickup. | Order.FulfillmentType = PICKUP. | Planned
TC-FR24 | FR24 | MVP | 1. Open menu. 2. Verify categories. | All FR24 categories present; menu loads. | Planned
TC-FR25 | FR25 | MVP | 1. Admin payment transaction report. | Payments linked to orders. | Planned
TC-FR26 | FR26 | MVP | 1. Admin create promotion. | Promotion saved with dates. | Planned
TC-FR27 | FR27 | MVP | 1. Admin deactivate promotion. | Not applied after end. | Planned
TC-FR28 | FR28 | MVP | 1. Admin feedback report. | Ratings/reviews aggregated. | Planned
TC-FR29 | FR29 | MVP | 1. Admin promotion effectiveness report. | Metrics with/without promo. | Planned
TC-FR30 | FR30 | MVP | 1. Admin reply to review. | Response visible with audit metadata. | Planned
TC-FR31 | FR31 | R2 | Guest checkout without registration. | Order completes; guest record by email/phone only. | Planned
TC-FR32 | FR32 | R2 | Place paid order. | Confirmation email received within 5 minutes. | Planned
TC-FR33 | FR33 | R2 | Apply valid and invalid coupon at checkout. | Valid reduces total; invalid rejected. | Planned
TC-FR34 | FR34 | R2 | Enter special instructions at checkout. | Instructions stored on order. | Planned
TC-FR35 | FR35 | R2 | Proceed to checkout. | ETA shown before payment. | Planned
TC-FR36 | FR36 | R2 | Track delivery order. | Live status updates for delivery. | Planned
TC-FR37 | FR37 | R2 | Complete order; submit rating. | One review per order. | Planned
TC-FR38 | FR38 | R2 | Reorder from history. | Items added to cart in one action. | Planned
TC-FR39 | FR39 | R2 | Search order history. | Matching orders returned. | Planned
TC-FR40 | FR40 | R2 | Change delivery address before submit. | Address validated and saved on order. | Planned
TC-FR41 | FR41 | R2 | Use forgot password flow. | Reset link works; old password invalid. | Planned
TC-FR42 | FR42 | R2 | Register with weak and strong passwords. | Weak rejected; strong accepted. | Planned
TC-FR43 | FR43 | R2 | Request nutrition on item. | Nutrition/allergen displayed. | Planned
TC-FR44 | FR44 | R2 | Pay with two configured methods. | Both methods succeed in test. | Planned
TC-FR45 | FR45 | R2 | Place order with notifications on. | Confirmation/status notifications sent. | Planned
TC-FR46 | FR46 | R2 | Complete usability task script on phone and desktop. | SUS >= 68 or 80% task success. | Planned
TC-FR47 | FR47 | R2 | Order below minimum or outside zone. | Order blocked with clear message. | Planned
TC-FR48 | FR48 | R2 | Five failed logins then login. | CAPTCHA or lockout triggered. | Planned
TC-FR49 | FR49 | R2 | Open support contact. | Support channel reachable/logged. | Planned
TC-FR50 | FR50 | R2 | Perform admin action; inspect audit log. | Action logged immutably. | Planned
TC-NFR1 | NFR1 | MVP | Enable 2FA for admin account. | 2FA required on admin login. | Planned
TC-NFR2 | NFR2 | MVP | Login and modify order; read audit log. | Events logged with user and timestamp. | Planned
TC-NFR3 | NFR3 | MVP | Inspect TLS and DB for PAN. | TLS 1.2+; no clear-text PAN. | Planned
TC-NFR4 | NFR4 | MVP | 100 concurrent users browse menu. | p95 < 500ms reads. | Planned
TC-NFR5 | NFR5 | MVP | Review 30-day uptime report. | >= 99.5% excluding planned maintenance. | Planned
TC-NFR6 | NFR6 | MVP | Execute backup restore drill. | RPO/RTO met per SYSTEM_REQUIREMENTS. | Planned
TC-NFR7 | NFR7 | MVP | Test 320px and 1920px layouts. | No horizontal scroll; usable layout. | Planned
TC-NFR8 | NFR8 | MVP | Run SUS survey with 5 users. | SUS >= 68. | Planned
TC-NFR9 | NFR9 | MVP | Count clicks browse to checkout. | <= 3 clicks primary path. | Planned
TC-NFR10 | NFR10 | MVP | Simulate gateway webhook retry. | Idempotent processing documented/pass. | Planned
TC-NFR11 | NFR11 | MVP | Architecture review scalability. | Pooling and scale path documented. | Planned
TC-NFR12 | NFR12 | MVP | Measure place-order and menu load. | p95 within REQUIREMENTS targets. | Planned
TC-NFR13 | NFR13 | MVP | Change order status; measure dashboard. | Update within 10 seconds. | Planned
TC-NFR14 | NFR14 | MVP | Smoke test Chrome last 2 majors. | Pass functional smoke. | Planned
TC-NFR15 | NFR15 | MVP | Smoke test Edge last 2 majors. | Pass functional smoke. | Planned
TC-NFR16 | NFR16 | MVP | Smoke test Firefox last 2 majors. | Pass functional smoke. | Planned
TC-NFR17 | NFR17 | MVP | Smoke test Safari last 2 majors. | Pass functional smoke. | Planned
TC-NFR18 | NFR18 | MVP | Search with 500 items. | p95 <= 3 seconds. | Planned
TC-NFR19 | NFR19 | MVP | iOS 15-17 mobile web smoke. | Critical flows pass. | Planned
TC-NFR20 | NFR20 | MVP | Run WCAG 2.1 AA automated + manual sample. | No critical violations on customer flows. | Planned
TC-NFR21 | NFR21 | MVP | Annual failover drill. | Failover within 60 minutes. | Planned
TC-SYS-RET | DRRD1-7 | MVP | 1. Delete customer account (FR3). 2. Verify PII purge/anonymization. 3. Confirm order history per legal retention. 4. Review audit entries. | Retention behavior matches ORD and SRS; no unauthorized PII remains. | Planned